## Project Management
Fibonacci Estimation Methodology: We used fibonacci numbers to assign a complexity value to the features then assigned those features to two team members who would own the definition and implementation of that feature into the game. The fibonacci value of the feature loosely maps to the expected amount of hours expected to complete that feature.
Project Feature Backlog |  |  |  | Project Metric | QTY | Pair | Team Members | Allocated Points
Feature | Fibonacci Value | Assigned to | Status | Total Features | 11 | Pair 1 | Alice & Audrey | 3
Initiatializing project and setting up node | 3 | Pair 1 | Complete | Total Fib Points | 19 | Pair 2 | Lilly & Heidi | 8
Build 10x10 Grid | 1 | Pair 2 | Complete | Completed Features | 11 | Pair 3 | Aayush & Aiman | 5
Implement the click / discover checking | 3 | Pair 2 | Complete | Progress | 100% | Pair 4 | Zain & Ibaad | 3
Implement flagging a cell | 1 | Pair 2 | Complete
Implement clicking bomb / game over | 3 | Pair 2 | Complete
Gameover screen | 1 | Pair 3 | Complete
Start game screen | 2 | Pair 3 | Complete
UI Color | 1 | Pair 3 | Complete
Grid Color | 1 | Pair 3 | Complete
QA / Stress Testing | 2 | Pair 4 | Complete
Requirments Testing | 1 | Pair 4 | Complete

## Meeting & HourLogs
Actual Hours Log |  |  |  |  | Meeting Notes Log |  | Template: Team Meeting Template
Date | Contributor | Feature | Hours Logged | Task Description | Date | Meeting Title | Meeting Notes Link | Attendees
2026-09-16 | Aiman | UI / Color | 1.5 | Making the site aesthetic | 2026-09-10 | First Team Meeting with TA | https://docs.google.com/document/d/1S-KSqvwwIgeksEfHW6qrfTxUzulBdwvsc6gFJ_M_BP0/edit?usp=sharing | Everyone
2026-09-16 | Aayush | Start Screen | 1.5 | Designing a starting screen | 2026-09-14 | Meeting to Discuss Beginning Implementation and Planning | https://docs.google.com/document/d/1Cd2t9ZLg3GvTW0GskIOiDQQ4_XYBvxty_QXzso5MTAQ/edit?usp=sharing | Audrey Facer, Heidi Schieber, & Lilly Tran
2026-09-15 | Heidi | Game Logic | 2 | Implemented logic for revealing and flagging cells. | 2026-09-14 | Meeting to Discuss Project Management | https://docs.google.com/document/d/14IqMExp7iZxjezWVzjQ4d8FsJKyb-OEoyftRKtI7gx0/edit?usp=sharing | Audrey Facer & Aiman Boullaouz
2026-09-14 | Audrey | Project Skeleton | 1 | Initialized github repository, created files, organized project. | 2026-09-17 | Second Meeting with TA | https://docs.google.com/document/d/1pfOkppq5oWuRb4YsPT5QtBxJQhhe2kRM8Na6cTXZPwE/edit?usp=sharing | Everyone
| Audrey | Documentation | 2
2026-09-15 | Lilly | Game Logic | 2 | Randomly generating mines around the mine and ensuring that the first cell is safe
2026-09-16 | Lilly | Game Logic | 1 | Checking the status of the board and if the player has won
2026-09-14 | Alice | Data Model Infrastructure | 3 | Helped set up files and made types.ts which sets up the data model of the game.
2026-09-20 | Ibaad | QA Testing | 2 | Created test casses and tested to see if they passed as well as looked over the requirments and checked if it fits witht he game logic
2026-09-20 | Zain | Requirments Testing | 1 | Verified product me assignment requirments